## Sheet1
# | Head | Domain | Projects | Phase | Start date | End date | What has been implemented | Business Interaction (Is Business involved, are they using it, etc.)
1 | Zakariyah | Finance | RV 2.0 |  | 2025-05-01 | 2025-10-04 | All Al Futtaim Brands (excluding AFE)
2 | Zakariyah | Finance | RV 3.0 - NEV |  | 2026-01-01 | 2026-12-31
3 | Zakariyah | Finance | Retail Sales Forecasting | Phase 1 - Toyota, Lexus | 2026-01-01 | 2026-09-30
4 | Zakariyah | Finance | Retail Sales Forecasting | Phase 2 - BYD, CDJR | 2026-10-01 | 2026-12-31
5 | Zakariyah | Finance | Digital Auto Finance (Blue - AutoHub) |  | 2025-01-01 | 2026-06-30 | - POC were completed with Emirates NBD, Emirates Islamic Bank, and Abu Dhabi Islamic Bank, with successful transfer of customer information and loan eligibility offer. POC implemented in Toyota - BYD - Automall DFC showrooms with 2 sales executives each - The UI/UX documentation covering the full end-to-end journey was developed and shared with Blue, AFS, and GTDP. Comprehensive user stories documentation for the full journey was created, finalised, and distributed to Blue, AFS, and GTDP. Handover sessions to AFS to be completed before 27th February 2026. | AFA - Dmitrii B AFA - Edmond M AFA - Lisa K AFS - Omar H AFS - Anil N AFS - Stephen M GTDP - Renzy M GTDP - Rethabile S Blue - Rabab M Blue - Geeta R
6 | Zakariyah | Finance | Predictive Price Elasticity AI |  | 2025-06-09 | 2026-06-30
7 | Roberto | Finance | Price Build Up / VME Analysis | Toyota, Lexus, BYD UAE | 2025-06-01 | 2025-11-15 | V.1. Implemented | Kick-off with Business on 20 January 2026
8 | Roberto | Finance | Price Build Up / VME Analysis | Honda, BYD KSA | 2025-11-16 | 2026-06-15 | V.1. Implemented | Handed over to Robert
9 | Roberto | Finance | Price Build Up / VME Analysis | CJDR Volvo KSA, OMASCO, DOMASCO | 2026-06-16 | 2026-12-31 | V.1. Implemented | Handed over to Robert
11 | Shivani | Marketing | MMM - Lexus | Q3 2025 | 2025-09-01 | 2025-09-30 | Delivered marketing contrinution report | Katib & team using the MMM output to report media performance
12 | Shivani | Marketing | MMM - Lexus | Q2 2026 | 2025-07-01 | 2025-07-10 | Q3 sales forecast | Supported Katib & team in calculating monthly sales forecast for Q3 given sales cycle seasonality, external factors & media budgets. The calculated forecast had an average accuracy of ~98%.
14 | Shivani | Marketing | Tactical & channel level budget optimization & scenario planning | Q4 2025 | 2025-10-01 | 2025-10-31 | TY & LX media budget planning based on the sales target, scenario testing with budget revisions, Optimal budget split recommendation between tactical & Brand campaigns | Katib & team used the budget recommendations & planned scenarios for their Annual 2026 budget approvals & QRMs
15 | Shivani | Marketing | Offline events & activations KPI setting TY & LX | Ongoing |  |  | Supporting Offline events & activations planning team with the right KPI & targets against them based on the type of activation & post activation performance analysis. | Mazeen Saab & Brand expereince team from TY & LX using the recommendations for their evenets objective setting & performance reporting
16 | Shivani | Marketing | Monthly media leads target setting (TY, LX, Automall) | Ongoing |  |  | Monthly media leads target setting & iterative adjsutments based on the pacing & seasonality post performance evaluation | Ongoing monthly engagement with Assaad & Karim, TY & LX marketing managers & Katib
14 | Shivani | Marketing | MMM - BYD UAE | Q4 2025 | 2025-12-01 | 2025-12-31 | BYD UAE MMM completed & the output used for 2026 budget setting & scenario planning | Tareq, Morgane & Roxanne used the budget split recommendations for the FY 2026 planning. Additionally Brand Health KPIs were also calculated to propose upper funnel targets for all oflline activations required to hit the sales target.
16 | Shivani | Marketing | MMM - BYD KSA | Q2 2026 | 2025-06-01 | 2025-06-30 | Delivered marketing contrinution report for BYD KSA. Did three models for them - 1. Media contrinution on sales 2. Media contrinution on Brand equity & its indirect impact on sales 3. Impact of other digital channels in driving search & impact of OOH deep dive on Brand building & sales | Using MMM output H2 media budgets & projected sales target were calculated Recommendations were used by Roxanne for H2 budget setting.
17 | Shivani | Marketing | Launch budget setting - Denza & Yangwang | Q4 2025 | 2025-10-10 | 2025-11-23 | Deployed a new method for calculating brand equity targets, digital & offline budget splits against the sales target in the absence of any historical or benchmarking data. | Roxanne, Tareq & Alieldin Eltamimi use the budget recommendations to propose their media budgets, set CPL targets for the agency & Brand health targets for the events team.
18 | Shivani | Marketing | MMM - Honda | Q4 2025 | 2025-11-01 | 2025-11-30 | MMM completed for Honda, output of the model used to calculate 2026 annual media taregts | Joel, Honda marketing manager, used the targets for 2026 annual planning & marketing budget setting.
19 | Shivani | Marketing | Honda - Offline campaign KPI setting | Q3 2025 | 2025-09-01 | 2025-09-10 | Supported KPI setting strategy for the offline campaign to assign agency right targets in the absence of direct performance attribution against leads. | Supported Honda marketing manager, Joel on KPI setting for the agency.
20 | Shivani | Marketing | Volvo - VIP Event | Q4 2025 | 2025-09-01 | 2026-09-30 | Supported Volvo team in identifyng the target audience segment, arriving at the safe data sharing method alignment, getting the data sharing agreement in place with the group & ADO and finally preparing the data segment as per requirement to be shared with the vendor. | Worked with Marketing manager Mridual and Lee Parker to facilitate the VIP event for Volvo
21 | Shivani | Marketing | Volvo - Annual budget setting | Q4 2025 | 2025-12-01 | 2025-12-31 | Delivered media targets & overall leads targets for Volvo for FY 2026 against their annual sales target & ran several revisions to arrrive at the final output. | Worked with Mridula, marketing manager on Volvo for her 2026 media budgets & target setting
22 | Shivani | Marketing | Automall - 2026 budget setting | Q4 2025 | 2025-10-01 | 2025-10-31 | Calculated required media budgets, channel split & a split by tactic based on 2026 sales targets. Supported in pivoting marketing strategy in diverting offline budgets to social media & calculated multiple impact sceanrios to finalize the approach. | Worked with Carlos & Wally, automall marketing manager
23 | Shivani | Marketing | Automall - Campaign performance evaluation | Ongoing |  |  | Ongoing support in measuring the uplift of campaigns - both offline & digital or third party vendors | Ongoing workstream with Wally, automall marketing manager
20 | Shivani | Marketing | MMM - Automall | Q1 2026 | 2026-01-01 | 2026-01-31 | MMM for FY 2025 due to be delivered by 20th January | Model output currently under review with Wally, marketing manager & model iteration based on additional requirements in progress.
21 | Shivani | Marketing | Automall - Pausing LeadGen on Social media | Q4 2025 | 2025-11-01 | 2025-11-30 | Worked with Automall marketing manager to readjust the leads targets for both media & direct to test a pilot case study on redirect budgets from LeadGen forms to web leads form. | Ongoing workstream with Wally, automall marketing manager
22 | Shivani | Marketing | Automall - Data sharing with CarSwitch | Q4 2025 | 2025-12-01 | 2025-12-31 | Supported Automall marketing manager in getting the data sharing approvals & setting up daily buying leads for Abu Dhabi with Carswitch | Ongoing workstream with Wally, automall marketing manager
23 | Shivani | Customer | CEC - monthly campaign data sharing for aftersales campaigns (All Brands) | Ongoing |  |  | Monthly target segment creation for 15+ campaigns across all brands based on the qualification criteria for the CEC | Carmeline & Jefferson from CEC & Autocenter. Eliminated manual work by automating the offer eligibility rules post alignment with the Brand teams.
24 | Shivani | Customer | CRM - monthly Churn campaigns (All Brands) | Ongoing |  |  | Monthly high propensity to churn customer list sharing across all brands for the CRM campaign | CRM brand managers
| Shivani | Customer | CRM - Quarterly repurchase campaign target list (All Brands) | Ongoing |  |  | Quarterly segment idenfictaion & data sharing for the repurchase CRM campaign for all brands | CRM brand managers
25 | Shivani | Customer | CRM - adhoch data requests (All Brands) | Ongoing |  |  | Data segment identification & data sharing based on requirements | All brands (CRM managers)
26 | Shivani | Customer | EMARSYS CRM Monthly Report_Opened | Ongoing |  |  | Validation and resolution of any reporting issues | CRM brand managers
27 | Shivani | Customer | CRM Emarsys Coms Performance | Ongoing |  |  | Maintenance support to address data issues, platform changes, or discrepancies if reported. | CRM brand managers
28 | Shivani | Customer | CRM Consent and Unsubscribe | Ongoing |  |  | Exceptions handling
29 | Shivani | Customer | EMARSYS CRM Report - MRS Journey | Ongoing |  |  | Report maintenance & exceptions handling
30 | Shivani | Customer | Repurchase Campaign Report Emarsys | Ongoing |  |  | Report maintenance & exceptions handling
31 | Shivani | Customer | Dataflow - GA Data Automation & CRM GA report | Ongoing |  |  | Report maintenance & exceptions handling
32 | Shivani | Customer | Customer Lifetime value analysis |  |  |  | Colated B2C customer data across all touchpoints to 1. calculate total number of unique customers per brand 2. Calculate CTV by brand 3. Average customer lifetime 4. Average Vehicle lifetime value per brand 5. Cross-Brand repurchase behavior | Results shared with Aftersales & AFM stakeholders. Insights are being utilized for aftersales & repurchase offer design, Model recommendation for repurchase campaign etc.
33 | Shivani | Customer | Resolicitation campaign | Ongoing |  |  | Customer behavior analysis on repurchase across all brands and changing trends analysis to arrive at the target segment definition for the resolicitation campaign. Created business case for the campaign & estimated the benchmarks for performance evaluation. | Worked with Jacques, STO team, CRM, CEC team & Carlos to redesign the resolicitation campaign strategy. Sharing target list with the CRM for every camapign Ongoing performance evaluation & reporting
34 | Shivani | Customer | Customer segmentation | Q4 2025 |  |  | Identified 12 behavioral customer segments across all Brands that can be directly used for Marketing communications. Next, we are in the process of collecting requirements from the business to adjust the segments accordingly. | Once the segments are finalized, we will work with the Brands to draft a bespoke communication stratgey for each segment with an objective to uplift CLTV.
35 | Shivani | Customer | Churn Prediction | Q4 2025 |  |  | Two churn models were created : 1. Aftersales churn prediction for the next scheduled vist (All Brands) 2. Customer churn prediction within one year (All Brands) | Aftersales churn model was stress tested with hstorical data & pilot was used for December month's campaign Jefferson (Aftersales) approved of the model & asked to add some additional features for the next scheduled model training.
36 | Shivani | Customer | CEC campaign list automation Dashboard | Q4 2025 |  |  | Selfserve dashbaord created for 15+ CEC aftersales campaign for TY, LX & Honda. CJDR - work in progress | Aftersale team stress-testing the automation output
37 | Shivani | Customer | Customer journey mapping - Customer 360 | Q4 2025 | 2025-12-01 | 2026-01-23 | Customer journey mapped against the KPIs, data availability, source, data table & data products name & flagged the missing parts of the journeys that are not being captured. Assigned order of priority on the missing parts based on the business use cases & importance.
22 | Shivani | Marketing | Data-driven Digital Attiribution |  | 2026-07-01 | 2026-12-31
23 | Shivani | Marketing | Lead Target and Marketing Budget Optimization |  | 2026-01-01 | 2026-12-31
24 | Shivani | Marketing | Precision Marketing with GenAI | Phase 1 - AI Ads Content Lab | 2026-07-01 | 2026-12-31
25 | Shivani | Marketing | Precision Marketing with GenAI | Phase 2 - A/B Testing Campaign Conversion Optimization | 2026-01-01 | 2026-06-30
26 | Shivani | Customer | Customer Re-scolicitation / Next Best Model Recommendation |  | 2025-08-11 | 2026-06-30
27 | Shivani | Customer | Churn Prediction |  | 2025-06-01 | 2025-11-30
28 | Shivani | Customer | Customer 360 |  | 2025-09-01 | 2026-06-30
29 | Roberto | Customer | Voice of Customer | Phase 1 - Call center | 2025-09-15 | 2026-06-30 | V.1. Implemented | POC with Business; Weekly meetings with stakeholders to improve the POC and incorporate their feedback
30 | Roberto | Customer | Voice of Customer | Phase 2 - Social Media, Surveys, WhatsApp, etc. | 2026-07-01 | 2026-12-31
31 | Zakariyah | Customer | CLTV | Phase 1 - Descriptive | 2025-10-01 | 2026-06-30 | Shivani (Ahmed Yehia)
32 | Zakariyah | Customer | CLTV | Phase 2 - Predictive | 2026-07-01 | 2026-12-31 | Not Yet Started
33 | Zakariyah | Operations | Predictive Maintenance AI Engine (RTA Buses) |  | 2026-07-01 | 2026-12-31 | Not Yet Started
34 | Zakariyah | Operations | Freight Forwarding Cost Optimization |  | 2026-07-01 | 2026-12-31
35 | Zakariyah | Operations | Stock Mix Optimization | Phase 1 - Used cars buying and selling price
36 | Zakariyah | Operations | Stock Mix Optimization | Phase 2 - Used cars stock mix | 2026-07-01 | 2026-12-31
37 | Zakariyah | Operations | Stock Mix Optimization | Phase 3 - New cars stock and car feature mix recommendation
38 | Zakariyah | Operations | VLTV | Phase 1 - Descriptive
39 | Zakariyah |  |  | Phase 2 - Predictive | 2026-01-01 | 2026-06-30
40 | Zakariyah | AI | Agentic Lead Scoring 2.0 |  | 2026-01-01 | 2026-06-30
41 | Zakariyah | AI | Agentic and Conversational AI | Phase 1 - BYD UAE/KSA, Toyota Chatbots | 2025-03-01 | 2025-12-31 | Outbound Workflow based: Lead Reactivation Bot 1. Polestar: Live 2. Toyota: Planned February 2026 live 3. BYD KSA (Paused: Live between March - November 2025): Planned February 2026 live Note: Previous Lead Reactivation bot was paused due to migration to Infobip Orchestration platform to ensure no clash with inbound AI Agent Inbound Agent (Conversational + Workflow based): Live 1. BYD UAE: WebSDK & WhatsApp 2. BYD KSA: WebSDK & WhatsApp 3. Toyota: WebSDK In Progress 1. Automall WhatsApp: Planned February 2026 live 2. Toyota WhatsApp: Planned February 2026 live 3. Lexus WebSDK & WhatsApp: Planned March 2026 live | Toyota - Katib B Lexus - Katib B BYD UAE - Tareq E BYD KSA - Roxane M Automall - Mohamad N CEC - Reuben P COE CX - Mohamed G
42 | Zakariyah | AI | Agentic and Conversational AI | Phase 2 - Honda, Lexus, Jeep, CDJR, Automall, IE Chatbots | 2026-01-01 | 2026-09-30
43 | Zakariyah | AI | Agentic and Conversational AI | Phase 3 - Conversational AI Agents | 2026-01-01 | 2026-12-31
44 | Zakariyah | AI | Agentic and Conversational AI | Customer Support Agent
45 | Zakariyah | AI | Agentic and Conversational AI | Sales Agent
46 | Zakariyah | AI | Agentic and Conversational AI | Booking Agent
47 | Zakariyah | AI | Agentic and Conversational AI | Aftersales Agent
48 | Zakariyah | AI | Agentic and Conversational AI | Brokerage / Leasing Agent
49 | Zakariyah | AI | Agentic and Conversational AI | Used cars Agent
50 | Zakariyah | AI | Agentic and Conversational AI | Loyalty & Retention Agent
51 | Zakariyah | AI | Agentic and Conversational AI | Re-scolicitation Agent
52 | Zakariyah | AI | Agentic and Conversational AI | Phase 4 - Back-office AI Agents | 2026-01-01 | 2026-12-31
53 | Zakariyah | AI | Agentic and Conversational AI | Parts Procurement & Sales Agent
54 | Zakariyah | AI | Agentic and Conversational AI | Inventory Analyst
55 | Zakariyah | AI | Agentic and Conversational AI | Social Media Analyst
56 | Zakariyah | AI | Agentic and Conversational AI | Market Researcher
57 | Zakariyah | AI | Agentic and Conversational AI | Industrial Equipment Quotation Agent
58 | Zakariyah | AI | AIP |  | 2026-10-01 | 2026-12-31
59 | Roberto | Data | SAP Rise Migration |  | 01.01.2025 | 30.08.2025 | Completed: SAP Migration from IS Auto to S4 Hana Project - Spearheaded the NON-SAP report migration activities - Repointed 581 Alteryx Workflows - Completed UAT for 750 Alteryx Workflows Migrated Alteryx Servers from GDA to New Dedicated servers - Facilitated the migration of 759 Alteryx Workflows from GDA workspace to the group servers SAP BW Data Source Migrations - Performed UAT to 210 reports - Successfully migrated 6 Report suites with 447 report variants across 16 Entities
60 | Roberto | Data | IDP Migration | Phase 1 - GDP | 2025-09-01 | 2026-03-30 | Report Rationalization - reviewed 1539 reports across all reporting platforms (Alteryx, Tableau, SAP BW, SAP BO, Power BI, GDP Tables) completed
61 | Roberto | Data | IDP Migration | Phase 2 - Others (BW, Alteryx, etc.) | 2026-04-01 | 2026-12-31
62 | Roberto | Data | Dealer Performance Dashboard | Phase 1 | 2025-03-01 | 2025-10-15 | implemented; | Business signed off and using it
63 | Roberto | Data | Dealer Performance Dashboard | Phase 2 | 2025-10-16 | 2025-11-15 | implemented; | Business signed off and using it
64 | Roberto | Data | Data Factory / True Book | Sales | 2025-09-01 | 2026-12-31 | 42 Data Products have been developed; Deployment Activities - Created systems and process around deployment activities - Organized deployment review board - Weekly deployment started on the last quarter of 2026 - Deployed a total of 147 iterations for more than 50 data products and 23 PBI reports - Created QA test books for all reports released for deployments with 40 QA standard points - Implemented an average of 50 Test cases for every initial releases and 20+ test cases for version release | Business has been involved in UAT sessions
65 | Roberto | Data | Data Factory / True Book | Presales, Marketing | 2025-09-01 | 2026-12-31
66 | Roberto | Data | Data Factory / True Book | Aftersales | 2025-09-01 | 2026-12-31
67 | Roberto | Data | Data Factory / True Book | Cross-domain | 2025-09-01 | 2026-12-31
68 | Roberto | Data | Data Factory / True Book | Master | 2025-09-01 | 2026-12-31
69 | Roberto | Data | Data Factory / True Book | Customer | 2025-09-01 | 2026-12-31
70 | Roberto | Data | Data Factory / True Book | Stock | 2025-09-01 | 2026-12-31
71 | Roberto | Data | Data Factory / True Book | Finance | 2025-09-01 | 2026-12-31
72 | Roberto | Data | Data Factory / True Book | Purchase Orders | 2025-09-01 | 2026-12-31
73 | Roberto | Data | Data Factory / True Book | Targets | 2025-09-01 | 2026-12-31
74 | Roberto | Data | Data Operations / BAU |  | 2025-01-01 | 2026-12-31 | Demand Management Tool: - Training arranged for 507 employees with roughly 60% attendees turning up at the actual training session - Activated 500+ employees on the DMRT App - Total of 358 tickets closed from go live on October 2025 with an average of around 120 tickets served every month (User access, Report enhancement, Data extract, New report requests which are shared with the Data Product Owners for action) - Created 5 additional Workspaces to optimize performance and support streamlining activities - Consolidated production reports into a single production workspace - Implemented reporting standards on visualization, Report Level Security (RLS) and user access provisioning - Currently monitoring and maintaining more than 300 Alteryx workflows, more than 150 Tableau reports, 53 PBI dashboards and supporting business escalation for SAP BW reports
75 | Roberto | Data | Sales Funnel 2.0. |  | 2026-01-01 | 2026-12-31 | Work in progress
76 | Roberto | Data | Customer Master Data Quality